## SI RFP Vendor Questions
Note: This is for internal tracking of SI RFP vendor questions and responses for UCLA Health
# | Area (i.e. HCM, Payroll, Finance, SCM, Change, etc) | Questions for UCLA Health | UCLA Health Responses/Notes
1 | Implementation Partner RFP - Introduction Document | At the bottom of page 18 of the RFP it reads like it is referring to a different filename (“Cloud ERP Selection Requirements Workbook” vs. “ERP Implementation Partner Workbook.” I can’t find a reference to the “B1. Tech Issues > TECH-18” requirement in the 7140 files downloaded. I’m guessing it may be a remnant from the software selection RFP if there was an Accessibility section in it. | Please disregard the link reference and answer within your proposal: • Does the vendor portal meet UC accessibility requirements? Available at http://www.ucop.edu/electronic-accessibility/index.html
2 | General | Acknowledging the desired start date of Q1 2025, do you have a preferred go live date in mind? | The assumption is the project would likely be an ~18-20 month engagement, preceded by a 2-4 month “Phase 0” planning stage. The preferred go-live date is November 2026. UCLA Health is open to other considerations depending upon your methodology and implementation expertise.
3 | General | Have you identified use cases for utilizing Prism? If so, please elaborate on what those are. | One Prism use case has been identified so far. It involves consolidating financial reports from the three entities: Medical Center (Workday financials), FPG, and School of Medicine (SOM). FPG and SOM financials are housed in the Campus Financial System, and the data is shared via reports and spreadsheets. On a monthly level, the financial results from these three entities need to be consolidated to prepare a consolidated financial report for UCLA Health System.
4 | General | Have you identified use cases for utilizing Extend? If so, please elaborate on what those are. | No use cases were identified so far. Perhaps something will arise as we get into the solution design phase.
5 | General | For the below question, UCLA Health Cloud ERP Selection RFP Attachment Requirements workbook document cannot be found. "Please provide an answer (Yes/No) to the below requirement in the UCLA Health Cloud ERP Selection RFP Attachment Requirements workbook. (B1. Tech Issues > TECH-18)." | Please disregard the link reference and answer within your proposal: • Does the vendor portal meet UC accessibility requirements? Available at http://www.ucop.edu/electronic-accessibility/index.html
6 | Strategy | Have you defined your Vision, Guiding Principles, Objectives, Value Statements, and Success Metrics? | Vision, Guiding Principles, Objectives, Value Statements, and Success Metrics have not been defined yet for the ERP program.
7 | Strategy | Have you defined your Governance Structure including roles and responsibilities, decision making authority, and escalation paths? | Nothing specifically has been defined for the Workday project yet. However, we typically follow a Project Organization Structure comprising of multiple layers: - Executive Steering Committee comprising of org-wide executives - Project Governance Committee comprising of Departmental and Operational leaders - Workstreams comprising of SMEs from respective areas
8 | Strategy | Do you intend to change your Service Delivery Model as a result of your implementation? If so, have you defined that future-state Service Delivery Model? | UCLA Health is open to changes in the Service Delivery Model as a result of implementation. This has not been defined yet. We will look to an implementation partner for guidance.
9 | Strategy | Do your Employees and Managers currently use Self-Service? Do you intend to keep the same level of self-service with Workday or do you intend to expand it? | Employees and Managers use Self-Service today and are limited by existing application capabilities. As we move into Workday, we plan to expand self-service capabilities given the platform's rich features.
10 | Strategy | Do you know where all your legacy data is stored, and do you have a plan for extracting it and validating it for your data conversions? | All ERP legacy data is stored within Lawson. A few years of legacy data will be converted into Workday as part of data conversions. We expect that the remainder of the legacy data can be stored in archival database.
11 | Strategy | Do you have a strategy for sharing information to downstream internal and external systems? Do you currently have systems in place that manage the sharing of information between internal systems? | Currently, data is shared downstream / upstream through point-to-point interfaces. Without procuring any additional middleware platform, if there is a way to deliver data using hub and spoke model, we are open to it.
12 | Strategy | Have you defined the future of reporting for your organization? Do you know which of your reports are mandatory/regulatory versus required to manage employees or required to do business? Do you know what reports or analytics your leaders would like out of the new system? | We will have to explore the reporting needs as part of the project discovery phase. We know what current reports are mandatory and regulatory.
13 | Strategy | Have you identified the challenges and gaps with your current processes? Have you documented all the touchpoints to processes outside of the system of record such as integrations, reports, or interpersonal communication? | All integrations with internal / external systems are shared as part of the RFP requirements. Several challenges and gaps with current processes are also rpovided within the RFP.
14 | Strategy | Have you recently, or do you have planned in the future, any M&A or Divestiture activity? | Recently, we had a merger with another hospital and it was the first one. In future, we may have more such mergers.
15 | Strategy | What type of post-implementation services would you foresee needing upon go-live? and for how long would you require each of these services? | We expect needing go live stabilization services for a period of 6 - 8 weeks.
16 | Organizational Change & Training | What internal change management, communications, and training capabilities/resources do you have or expect to have for this project? | UCLA Health recognizes that change management is crucial to the success of the engagement, and we are looking for your recommendation for the best way to approach it with a Workday implementation. Whether you lead/co-lead, handle all of it, “train-the-trainer”, or some blended approach. We are very much looking for your recommendation on this one.
17 | Organizational Change & Training | How many internal, dedicated change management, communications and training resources will be provided for the Workday implementation? | We would look for you to describe the optimal way to organize the internal OCM team.
18 | Organizational Change & Training | Briefly describe your organization’s culture and estimated level of resistance to change/adoption of technology | UCLA Health is an Academic Medical Center that puts emphasis on learning and adopting changes to help improve patient care outcomes.
19 | Organizational Change & Training | Have you engaged end-users in a Change Champion network previously? | Many of our end users have undergone a major system change exercise as part of the Epic implementation.
20 | Organizational Change & Training | Will development of training materials (job aids, captivate simulation videos, PPTs, etc.) be created internally or by your partner? | This will likely be a joint developement effort with guidance from your team. We are very much looking for your recommendation on what works best.
21 | Organizational Change & Training | Do you have an internal training team that would be leveraged for a Train-the-Trainer approach? | There is an internal Training team for Epic and couple of such trainers can help with Workday training. We are looking for your recommendation on what works best.
22 | Organizational Change & Training | What are some past projects you’ve executed and how did they go? What were your pain points? | UCLA Health implemented Infor warehouse management system (WMS) recently. Some pain points included technical isssues and integration complexities with other systems. Infor customer support was also insufficient in addressing and resolving challenges quickly.
23 | Organizational Change & Training | Have you conducted any stakeholder or readiness assessments related to this initiative? If so, what were the results? | No stakeholder or readiness assessments have been used before.
24 | Testing | Please provide information on number of reports and interfaces that are needed to be included in testing scope. | Please refer to RFP requirements and information provided in the RFP implementation partner workbook. Further information on reports has not yet been determined.
25 | Testing | Can you please confirm if there are any existing (manual & automation) test case repository? If available, please share the module wise count | There is a repository of Lawson test cases.
26 | Testing | Please specify the test management / defect management tool that is currently being used by UCLA? | Excel spreadsheets are being used to support test / defect management.
27 | Testing | For test automation, would you please let us know the tool of choice. | We would rely on the implementation partner to provide a recommendation on the testing tool.
28 | Testing | Please specify the regression testing tool that is currently being used by UCLA. | In a limited capacity, our Testing team uses Eggplant software for regression testing.
29 | Automation | Are you currently utilizing any RPA tools within your organization? If so, which specific RPA tool is preferred for this RFP scope? | No RPA tool being used.
30 | Automation | Beyond Workday's functionalities, are you open to exploring RPA or other intelligent automation solutions to further streamline your finance and SCM processes? | We are open to hearing recommendations.
31 | Automation | Do you currently leverage any reporting dashboards to visualize your data? If so, could you provide a brief overview of the dashboards you utilize? | Nothing specific for Lawson. In-house today, we have Tableau and Power BI tools for data visualizaton.
32 | Automation | Are there any recurring scenarios in finance or SCM where data analysis or rule-based decisions could potentially be automated? | Potentially yes, there are recurring scenarios where data analysis or rule-based decisions could be used.
33 | Automation | Following the Workday migration, what are your top priorities for improving efficiency and accuracy within your finance and SCM functions? | This is to be discussed as part of project discovery.
34 | Automation | OCR/IDP - What kind of documents or process are prime candidates for automation using OCR? For e.g.: requisitioning, purchasing, contract administration, expense reporting. | Prime candidates for automation today include invoices, packing slips, and backup documentation for journal entries (scanned in)
35 | Automation | For each of these areas (Accounts Payable, Capital Projects, Cash Management, and Bank Reconciliations), could you please detail any specific tasks or processes that you have identified to automate or support through AI, machine learning, and digital assistant functionalities? Can Co-Pilot be considered for automating or supporting some of these tasks? | This is to be discussed as part of project discovery.
36 | Automation | For Financial and statistical reporting requirements, can you consider designing a solution using Power BI for data visualization and Power Apps for user interaction? | We would prefer to use Workday tools primarily for reporting visualization.
37 | Automation | Are you currently using a cloud platform like AWS, Azure, or GCP for your operations? If so, would you prefer to leverage the same platform for automation scope of work? | Many areas in UCLA Health IT use the cloud platforms listed here, mostly AWS and Azure. The Lawson application team does not use any cloud platform.
38 | Minimum Qualification Standards | There is a list of minimum qualification standards on page 19. Please confirm that there is no additional vendor information required in the "Instructions for Submitting Information" section for vendors to demonstrate that they meet the minimum qualifications. | These are minimum requirements. There may be additional requirements as the evaluation progresses.
39 | Issuing Office and Communications | The RFP document indicates that "All communications, including any requests for clarification concerning this RFP should be address in writing to...UCLA Health Procurement." Please provide guidance on what communications is expected and/or allowed with Chartis directly. | Please communicate directly with UCLA Health Procurement. Chartis will support the UCLA Health Procurement team in response.
40 | Evaluation and Method of Award | The last sentence of the first paragraph is incomplete: "In addition to material provided in the submission, or may request oral presentations, additional material, information, or references from the Supplier and others." Please clarify what to expect in addition to the materials provided in the submission. | In addition to the materials expected in the submission, UCLA Health may request additional informations. UCLA Health will notify you in advance for this needed information.
41 | Evaluation and Method of Award | Please confirm whether an award decision can be made with the evaluation of the written submission without vendor presentations. | Vendor presentations may contibute to an award decision.
42 | Evaluation and Method of Award | Please confirm that the point weighting is equal across all factors. | Point weighting will vary across factors and is subject to change by UCLA Health.
43 | Response to F. Costs Worksheet | Please confirm that a final contract award could be made for a firm fixed price contract. If a firm fixed price contract is possible, please confirm that the "Response to F. Costs Worksheet" information will be used for price evaluation purposes only during the RFP process. | Yes, confirmed - firm fixed price contract is possible and the F. Costs worksheet will be used for price evaluation during RFP proces
44 | Project Duration | For planning purposes, please confirm the expected project start date and go live date assuming the "Q12025 target start of implementation" in the Timeline of Key Events. | The assumption is the project would likely be an ~18-20 month engagement, preceded by a 2-4 month “Phase 0” planning stage. Preferred go-live date is November 2026. UCLA Health is open to other consideration depending upon your methodology and implementation expertise.

## 7-11-24 Questions
Note: This is for internal tracking of SI RFP vendor questions and responses for UCLA Health
# | Area (i.e. HCM, Payroll, Finance, SCM, Change, etc) | Questions for UCLA Health | UCLA Health Responses/Notes
1 | Scope (Appendix A) | Can you list out all the Workday modules you plan to deploy. For example, on page 11, you list Asset Management, but it isn't listed on Appendix A. Want to make sure we address the correct set of modules. | Please refer to the Appendix A: Workday subscription table for the Workday products to be deployed.
2 | Scope (Appendix A) | Please share any specific Extend use cases you have identified during product demos. | No use cases were identified so far. Perhaps something will arise as we get into the solution design phase.
3 | Scope (General) | Can you provide a comprehensive list of applications you plan to sunset, and those which you plan to retain | This list of applications to sunset and retain has yet to be finalized.
4 | Change Management (OCM page 6) | Do you use a Digital Adoption Platform (DAP) like WalkMe/Maverick? If no, are you considering implementing with this project? | No intention to use a DAP today. Perhaps this will be considered as we get into the design phase.
5 | Change Management (OCM page 6) | Do you have an established Change Managent Organization and will they be staffed to this project? | No change management organization exists today. We would look for you to describe the optimal way to organize an internal OCM team.
6 | Supply Chain (SCM) | What point-of-use solution do you use today? | No existing POU and not in scope for this engagement.
7 | Supply Chain (SCM) | Do you have multiple item masters? | No, one Item Master only.
8 | Supply Chain (Key Statistics Page 7) | You seem to have over 5000 vendor contracts. Can you please provide some context around the types of contracts? | Contracts cover products, purchase services, professional services and consignment agreements.
9 | Tech (General question) | Do you have data warehouses or data lake that we should account for? | No data warehouses or data lakes to account for.
10 | Tech (General question) | Do you have more than one instance of Lawson today? If yes, how many instances of Lawson do you plan to replace with Workday? | Currently we have 1 instance with 2 product lines (1 for Medical Center and 1 for FPG).
11 | Tech (General question) | Do you have any appetite for taking on integration or report design and development? Will the technical integration and report development be a joint effort between our team and UCLA IT team? If so, what percentage of this work do you anticipate your IT team will handle? | Yes, UCLA Health is open to taking on integration or report design and development. We look to your guidance on the optimal way to split this effort.
12 | Tech (General question) | What middleware do you utilize, and do we need to integrate it with Workday? | Currently, OpenShift is being used. Future state TBD.
13 | Data Cleanup (SCM and FIN) | Do you plan any significant master data cleanup or harmonization in advance of this project? | UCLA Health is open to recommendations on master data cleanup and harmonization in advance of this project.
14 | OCM | What internal OCM capabilities does UCLA Health have that can be deployed during the Workday program? | UCLA Health has gone through several transformational projects such as Infor WMS and Epic, navigating large scale change and training end users.
15 | SCM | Will there be any rationalization of POU systems or will all current POUs be in scope for integration? | No existing POU and not in scope for this engagement.
16 | SCM | A number of procurement applications are listed, will there be any planned rationalization across applications prior to integration to Workday? | UCLA Health is open to recommendations on procurement applications to rationalize prior to integration with Workday.
17 | Cyber Security | Have you undergone a cybersecurity assessment as you plan to move to Cloud ERP? If so, when was it completed? | No cybersecurity assessment has been completed as part of the plan to move to Cloud ERP.
18 | Tax | Please provide the number of transactions or dollar amount (or close approximation) processed in 2023 for the following processes in total for all legal entities: 1) Number of Form 1099 issued 2) Number of Form 1042-S issued 3) Number of B-Notices received 4) Total sales tax ($) charged on accounts receivable and non-patient billings 5) Total sales tax ($) paid on purchases (capital and non-capital) | Detailed tax-related volumes and dollar amounts will be provided to the vendor of choice. This data should not impact anyone's response.
19 | Scope Question | Could you please expand on the operations for the asterisked (*) in-scope items? What do you mean by "minor operations"? | These are operation areas that may be secondary in importance or covered by other applications e.g., Infor WMS but are called out for tie-in to Workday.
20 | Change Management | Does UCLA Health have an existing Change Management and Training team that will be committed to the Workday project? What is their level of experience in communications, change management, and training development and delivery? Do you use any automated tools/technology do you use for Training Development and Delivery? | No change management team has been committed to the Workday project yet. We would look for you to describe the optimal way to organize an internal OCM team. No automated tools/technology for Training Development and Delivery is used.
21 | Misc Questions | More clarity requested on following vendor interaction in future state with Workday. - Future state plan for payment interfaces: In-house Check printing, Label? - Future state plan for banking payment confirmation, fee statements, reconciliation, and credit card file interaction with banking and financial organization. - Any plan for Data warehouse, Reporting, Budgeting, and analytics systems consolidation/change for the interaction with Workday. - Future state interaction plan with Zoom, Office 365 from Workday. | Future state plans have been yet to be designed for all areas. Refer to interface guidance on what is known to be needed so far.
22 | PRISM | Are there any PRISM use cases already identified? (other than the consolidated reporting between Med Center, FPG and School of Medicine) | One Prism use case has been identified so far. It involves consolidating financial reports from the three entities: Medical Center (Workday financials), FPG, and School of Medicine (SOM). FPG and SOM financials are housed in the Campus Financial System, and the data is shared via reports and spreadsheets. On a monthly level, the financial results from these three entities need to be consolidated to prepare a consolidated financial report for UCLA Health System.
23 | Extend | Are there any Workday Extend applications already identified to be deployed by UCLA Health? | No use cases were identified so far. Perhaps something will arise as we get into the solution design phase.
24 | Reporting inventory | Is there a current consolidated listing of reports - by each system that can be shared. Alternatively, approximate volume of reports by functional area. | There is no existing list. Lawson has been in place 20+ years so there are a large number of reports.
25 | External Systems | What external accounting systems do FPG and NCHP use currently? | Kaufmann Hall and the Campus general ledger interface to Infor. There are no other ledgers.
26 | Expenses | What is the anticipated number of employees that will be submitting expenses via Workday? Is the expectation that employee expense reimbursements will be paid via UCPath or Workday FIN? | We have over 10,000 employees. However, we will likely have around 1,000 to 2,000 actual employees that with submit expenses. These payments will be paid via Workday FIN not UCPath.
27 | Technical - Integrations | What is your expectation of the effort split for integration development between UCLA Health and your Implementation Partner? E.g., we typically have shared development effort at a 50/50, 60/40, or 70/30 effort split between Huron and our clients, respectively. What is UCLA Health's current Identity Management system? What is UCLA Health's current authentication system (e.g., Authenticator, Duo)? | We would look for you to describe the optimal split of development effort for UCLA Health and implementation partner. Current IDM is OKTA and current authentication system is Duo.
28 | Technical - Data Conversion | Do you have IT staff prepared to develop the data extractions necessary to support data conversion activities? | Yes, UCLA Health does have IT staff to support data conversion activities. We would look for you to describe the optimal way for IT staff to prepare and support data conversion.
29 | Grants / Research | Are there any requirements to integrate to the UC BRAID research systems? To confirm, is Grants Management in scope? Has UCLA Health purchased Workday's Grants module? | Grants is not in scope
30 | Supply Chain Management | Will UCLA Health use the Workday Inventory Management Functionality for perpetual inventory and par replenishment or will INFOR WMS be used for all inventory transactions? | UCLA Health will leverage the Workday inventory management functionality whereever possible.
31 | Scope and Conversions - Projects | Does UCLA Health leverage billable projects, track non-capital projects and/or perform labor cost capitalization on projects? This information will assist with scope determination. | No, we do not do billable projects. We very rarely capitalize labor, but since HR is not in scope for Workday, we will not need to consider this.
32 | Conversion - Assets | Is UCLA Health expecting to convert non-depreciable (non real estate) and/or expensed assets? | No, we do not have non-depreciable (ex. Land) nor expensed assets.
33 | Change Management / Training | What change management, communications, and training resources is UCLA Health planning to dedicate to this initiative? Please characterize the role that UCLA Health's team will lead and execute these change adoption activities throughout the project lifecycle. | We would look for you to describe the optimal way to organize an internal OCM team for Workday implementation and partner with the implementation partner -- whether you lead/co-lead, handle all of it, “train-the-trainer”, or some blended approach.
34 | A. Vendor Response Questions, ADD-02 | The A. Vendor Response to Questions MS Excel spreadsheet item ADD-02 requests, "Please provide a copy of your master service agreement (and/or contract template)." Please clarify what is expected to be provided with this request given that the RFP package included the "UCTermsandConditions-080619.docx". | We are requesting a copy of the vendor's master agreement. UCLA's was supplied in the RFP documents.